## Preseason
EXAMPLE
Process Name Assign a name to the process that properly describes what you are defining |  |  | Scholarship Preseason
Timeframe When does the process begin and when does it end |  |  | Start: December 1, 20XX End: Feb 8, 20XX Scholarships Open Feb 10
Process Purpose (output) What is the end result of the process |  |  | Prepared to accept student applications for the Local Dollars for Scholars scholarships by: 1. Having scholarships ready, 2. Having student instructions available, 3. Spreading the news
| What - The action step that needs to take place | Why - The purpose of the step | How - The means of completing the action, any dependencies or requirements that must take place before | Who - The person that executes the action | When - The timeline this step needs to be completed
1 | Verify scholarships will be run |  | Confirmation of Donors and Funds Available with Awards Chair | Chapter Super Admin / Scholarship Manager | 2019-01-12
1 | Confirm with donors they will be supporting the named scholarship |  | Reach out to current named scholarship donors | Awards Chair | 2019-01-12
1 | Confirm with Treasurer that funds are available to support scholarships |  | Email Treasurer | Awards Chair | 2019-01-12
1 | Determine and set Open and Close Dates for scholarships
1 | Set up scholarships in system |  | Advance scholarships in ChapterNet and coordinate with the Awards Chair | Chapter Super Admin / Scholarship Manager | 2019-02-01
1 | Review setup of scholarships | Want to make sure the process of applying is correct so that the correct students are eligible to apply for the correct scholarhsips | - Review Open/Close Dates, Standard Restrictions, Eligibility Questions, Custom Questions, and Additional References. - Run a Test Student through the process. - Reach out to Scholarship America with Questions - Review Enhancement document to see if any changes impact our requirements | Chapter Super Admin / Scholarship Manager | 2019-01-31
1 | Review Positives and Room For Improvement notes from previous year |  | Compile list of scholarship season that needed improvement from the previous year | Awards Chair/Committee | 2019-12-01
2 | Create student instructions | To provide students with the exact requirements needed to apply for our scholarships | - Modify stock instructions Scholarship America provides in Affiliate Resources to align with Local Dollars for Scholars requirements Needs: - PowerPoint or Word, depending on which instructions we will modify | Scholarship Manager | 2019-02-01
2 | Make updates to instructions based on system changes/enhancements |  | Review Enhancement document found in ChapterNet | Scholarship Manager | 2019-01-28
3 | Website: update dates & information | Community touchpoint to inform students of when the application period is |  | Publicity Chair and Technology Officer (Website Admin) | 2019-01-01
3 | Website: provide student instructions | To provide additional references for students on how to complete the application & to provide our requirements | Need updated student instructions from the Scholarship Manager | Technology Officer (Website Admin) | 2019-02-04
3 | Provide student instructions to the high school |  | Need updated student instructions from the Scholarship Manager | Publicity Chair
3 | Craft and send message to the high school(s) about scholarships available and application dates | Community touchpoint to inform students of when the application period is |  | Publicity Chair
3 | Craft and send message to other media outlets about scholarships available and application dates | Community touchpoint to inform students of when the application period is |  | Publicity Chair
3 | Email students that have already created accounts in the system | Direct communication with student | Reports | Chapter Super Admin/ Scholarship Manager
3 | Meet with Senior Class for Scholarship Power Hour
3 | Post information on Facebook (DFS site or other groups)

## Season
WORKSHOP
Process Name Assign a name to the process that properly describes what you are defining |  |  | Scholarship Season
Timeframe When does the process begin and when does it end |  |  | Start: Scholarship Open Date End: Scholarship Close Date/Application Review/Scholarship Selection
Process Purpose (output) What is the end result of the process |  |  | Award scholarships to scholarship applicants 1. Verify all materials are submitted by students, 2. Score applications, and 3. Make award decisions
| What - The action step that needs to take place | Why - The purpose of the step | How - The means of completing the action, any dependencies or requirements that must take place before | Who - The person that executes the action | When - The timeline this step needs to be completed
1 | Create a Test Student and verify the applicatin process
1 | Inform and remind students during application period of the deadline
1 | Provide guidance, instructions, and encouragement on Essays
1 | Send email reminders students to "Apply" for the scholarships
1 | Go to the school to demonstrate application process
1 | Go to the school to answer questions
1 | Conduct a Scholarship Application Event
1 | Speak with students early about application process
1 | Go to the school to assist with filling out the application
1 | Set realistic expections
1 | Work with younger classes (9th - 11th grades) to start profile and update each year
1 | Email reminders to 1st year and 2nd year post high school students
1 | Review Scholarship Setup (Adjusted Weighted Score)
1 | Reach out to high school counselor and ask them to encourage students to apply
1 | Post information on Facebook page
1 | Conduct a FAFSA night
1 | Meet with POD Class (all seniors) 2 - 3 times during the scholarship application period
1 | Review scholarships before close to see if there are any with Zero applicants
2 | Score applications using the ChapterNet point system
2 | Find an outside individuals/volunteers to serve on Scoring Committee
2 | Schedule time for members to gather to score
2 | Assign/deligate application sections to be scored be separate board members
2 | Confirm all students are scored
2 | Print Paper App Anons
2 | Score applications with board in one night with Pizza
2 | Set up Evaluation Group in ChapterNet
2 | Assign appropriate access for scoring applications in ChapterNet
2 | Provide our rubric to committee members to score essays
3 | Provide student instructions for accepting their awards online
3 | Remind students that have not accepted their awards
3 | Send Award Letter to recipient (mail)
3 | "Notify Recipients" in ChapterNet to allow student to accept their award online
3 | Review scholarship criteria when making awards (Field of Study, Need vs. Merit, etc.)
3 | Remind students to send Thank You Letter/Note
3 | Remind students to upload photo into ChapterNet OR send photo to us
3 | Verify all students that apply (submit application) are awarded
3 | Enter awards in ChapterNet
3 | Hold Awards Ceremony at school
3 | Provide information to students and donors about the Awrads Ceremony
3 | Trust the Process

## Post season
TEMPLATE
Process Name Assign a name to the process that properly describes what you are defining
Timeframe When does the process begin and when does it end
Process Purpose (output) What is the end result of the process
| What - The action step that needs to take place | Why - The purpose of the step | How - The means of completing the action, any dependencies or requirements that must take place before | Who - The person that executes the action | When - The timeline this step needs to be completed